## Sheet1
Task Row | Task Name | Duration | Predecessors
1 | 1 Initiating
2 | 1.1 Stakeholder Identification | 1w
3 | 1.2 Stakeholder register completed | 0 | 2
4 | 1.3 Stakeholder management strategy completed | 0 | 2
5 | 1.4 Project charter | 1w | 2
6 | 1.5 Project charter completed | 0 | 5
7 | 1.6 Kickoff meeting | 3d | 2,6
8 | 1.7 Kickoff meeting completed | 0 | 6,7
9 | 2 Planning
10 | 2.1 Schedule | 5d | 5
11 | 2.2 Gantt chart completed | 0 | 10
12 | 2.3 Scope statement | 8d | 5
13 | 2.4 Initial scope statement completed | 0 | 12
14 | 3 Exeecuting
15 | 3.1 Deliverable 1 | 3w | 12
16 | 3.2 Deliverable 2 | 5w | 18
17 | 3.3 Deliverable 3 | 6w | 18
18 | 3.4 Deliverable 1 completed | 0 | 15
19 | 3.5 Deliverable 2 completed | 0 | 16
20 | 3.6 Deliverable 3 completed | 0 | 17
21 | 4 Monitoring and Controlling
22 | 4.1 Actual hours tracking | 0 | 20
23 | 4.2 Project documents updates | 0 | 20
24 | 4.3 Progress report 1 | 2d | 23
25 | 4.4 Progress report 2 | 2d | 23
26 | 4.5 Team review meeting | 0 | 24,25
27 | 5 Closing
28 | 5.1 Final project report | 4d | 18,19,20
29 | 5.2 Final project presentation | 4d | 18,19,20
30 | 5.3 Project completed | 0 | 28,29